## Hospital
Split Billing Implementation Plan
Date Start: Date Complete: | Covered Entity (CE): 340B ID: Verity Solutions Account Manager: Implementation Manager:
|  | Assignment Owner | Status | Completion | Notes: | ETA (internal)Min
Pre-Kickoff Evaluation | Receive Contracts |  |  |  |  | 5
| RSD sends completed Sales Questionnaire |  |  |  |  | 600
| Account has been approved for Implementation |  |  |  |  | 30
| Request and schedule Kickoff call with CE |  |  |  |  | 600
Kick Off Meeting | Welcome and Introductions |  |  |  |  | 5
| Review documents previously sent *Verity 340B Split Billing Spec *Verity 340B Site Profile *V340B SB Implementation *V340B Implementation Process Diagram |  |  |  |  | 15
| Review and confirm 340B Eligibility, OPA ID, Splitting sequence, shared accumulators… |  |  |  |  | 5
| Establish Client expectation of the migration from current AutoSplit data |  |  |  |  | 10
| Project overview and expectations |  |  |  |  | 10
| Milestone |  |  |  |  | 5
| Establish time line (60-90 day or extentuating circumstances) |  |  |  |  | 5
| Verity procedures *PO, loading transforms, reports, MoveIt location, URL, transactions… |  |  |  |  | 15
Identify the data spec that they will be using i.e., Verity data spec or current PARs transacitons from AutoSplit.
| Would the CE like to exclude NDC's from being migrated that have Last Used more than 6 month, 1 year, 2 years…. |  |  |  |  | 10
| Discuss with CE Verity's involvement with Wholesalers (switching EDI or apply for EDI accounts on behalf of CE, Wholesaler setup) |  |  |  |  | 5
| Discuss change management process to modify any aspect of the Implementation |  |  |  |  | 10
| CE signs off on Kickoff meeting via response or non-response (please document procedure |  |  |  |  | 5
Kick Off Meeting Completed | The CE has accepted all parts of the kick off. They understand that the Kickoff establishes the start date. |  |  |  |  | Milestone
Wholesaler Requirements for Verity | Notify Vendor and request accounts and EDI |  |  |  |  | 4800
CE Data Review | Request six month sample of transaction data in approved data specs |  |  |  |  | 5
| Review that transactions are in approved data specs |  |  |  |  | 30
Request Dev provide Mapping if Verity standard spec not used (special request reserved for established CE's )
| Request MoveIT for sFTP |  |  |  |  | 10
| Send sFTP credentials to CE *Encrypt email when sending username & password |  |  |  |  | 360
| Confirm SFTP connection with sample test data from CE |  |  |  |  | 2400
| Request Transforms from CE *Single mapping *Multiplier |  |  |  |  | 2400
| Review mapping *CDM to NDC are 1:1 *Jcodes *QCF |  |  |  |  | 480
| Sign off from CE on Transforms and Transactions |  |  |  |  | 30
CE & Vendor Requirements Completed | The CE's Vendor has been contacted and EDI accounts have been setup in Verity. A six month sample transaction file has been created by the CE and sFTP'd to the approved Verity location. The transactions and transforms file structures have been approved. |  |  |  |  | Milestone
Test Sample Transaction | Create Test Verity accounts |  |  |  |  | 30
| Create Test Verity user accounts for CE |  |  |  |  | 20
| Confirm a standard EDI832 catalog has been sent by Wholesaler then received and processed by Verity. (Also confirm other EDI or other types of files are sent/received) |  |  |  |  | 1200
| Load transforms |  |  |  |  | 5
| Load /process 6 months of sample data |  |  |  |  | 10
| Review and send accumulations, transforms, and unknowns to CE for review |  |  |  |  | 30
Repeat testing in Test Verity until CE approves of test accumulations
| Testing Verity signed/approved by CE |  |  |  |  | 30
| Set a Go Live in Production date. Send Launch schedule |  |  |  |  | 30
| Reach out to the Vendor to notify them of the EDI Launch date or have them switch the EDI of the legacy 340B Software to Verity. Confirm if there is going to be a representative available to assist on launch day. |  |  |  |  | 1200
Sampling & Testing Completed | A six month sample of transactions have been processed in Test Verity and the accumulations have been approved and signed off by CE. Vendor EDI connections have been tested and confirmed. The CE is sending transactions consistantly. Transforms have been processed and approved. The final test of current transactions and accumulations have been approved and signed off by the CE. |  |  |  |  | Milestone
Critical Operations (Recommended that these tasks are completed before Launch) | Confirm that CE has placed a large PO with Vendor. This should be large enough to sustain the CE in the case there are issues with the cutover to Verity. |  |  |  |  | 30
| IF a CE places a PO wait till the invoice for that PO has been processed in the legacy 340B software before switching EDI and pulling the final ITEM USAGE accumulator |  |  |  |  | 240
| Confirm Wholesaler has setup or switched the EDI to Verity after the invoice for the final PO has been processed. |  |  |  |  | 5
Pre-Launch in Production | Set up accounts in Production |  |  |  |  | 5
| Confirm SFTP files are running automatically into Production |  |  |  |  | 10
| Create CE user profile in V340B Production if not already done |  |  |  |  | 30
| Load CE's transforms from QA to Production |  |  |  |  | 5
Launch in Production | Load CE's approved transactions into Production |  |  |  |  | 5
| Review accumulators in Production |  |  |  |  | 30
Review Unknowns in Production
| Review accumulators with CE and get a final/approval sign-off |  |  |  |  | 30
| Have CE create a small PO on Wholesaler site and submit |  |  |  |  | 60
| Confirm Verity received and split order |  |  |  |  | 5
| Confirm that Verity sent and received EDI from Vendor (split POs, 850, 855, 810) |  |  |  |  | 360
| Review accumulators, split PO, and invoice reciept with CE and get sign off/ approval |  |  |  |  | 30
| Schedule CE training |  |  |  |  | 5
CE Training | Create user accounts |  |  |  |  | 10
| Train the CE users on Verity |  |  |  |  | 120
| Review splitting details of PO with CE |  |  |  |  | 30
| Review transforms (Crosswalks, multipliers, compounds, unknowns) |  |  |  |  | 60
| Introduce CE to account manager |  |  |  |  | 10
Covered Entity is live with the Verity Solutions Split Billing software | The Launch is complete and the CE is live on Verity Solutions split billing software. User accounts have been created, training is complete, and the Verity Solutions Account Manager has been introduced. A final sign off/approval from the CE is completed. |  |  |  |  | Milestone
Post Go Live | Verity continues to receive EDI from Vendor |  |  |  |  | 5
| Confirm all tasks are completed |  |  |  |  | 10
Monitor Feeds
[6 empty] | 12.9167 | Weeks